## Hatchet Troop
Timeline | POC | Tasks |  |  |  | NLT
Pre-Command Preparation (D-60 to D-1) | Operations/ Training/Supply |  | Review:
|  |  |  | Policy Letters | Appointment Orders | T-8
|  |  |  | In/Outprocessing Forms | Troop SOPs
|  |  |  | DTMS | Property Book
| BN Staff/Maint |  | Review: |  |  | T-7
|  |  |  | SQDN mission and METL | SQDN SOPs and Policy Letters
|  |  |  | SQDN ATG/QTG | SCO's Intent
| Supply |  | Meet and discuss COC inventories and TTPs for a successful inventory |  |  | T-6
|  |  | Give Supply Sergeant intent for change of command inventories |  |  | T-6
|  |  | Conduct Change of Command Inventories |  |  | T-6
| Ops |  | Order nameplate for building |  |  | T-4
|  |  | Prepare for CoC: Invitations, Speech, Timeline, Biography, Reception |  |  | T-4
| Outgoing CDR |  | Review/Discuss:
|  |  |  | CATS/EXEVAL results | QTBs | T-3
|  |  |  | USR | Inspection results | T-3
|  |  |  | Climate Surveys | Training Calendar | T-3
|  |  |  | UCMJ, Troop personality | Troop METL & Assessment | T-3
|  |  |  | Family Care Plans | MEDPROS | T-3
| Addtl Duty Prsnl |  | Review Additional Duty SOPs and Continuity Books |  |  | T-3
| BDE SJA/Legal |  | Meet and get to know in advance; figure out unit legal issues and rates |  |  | T-3
| 1SG |  | Develop draft Command Team Philosophy with 1SG |  |  | T-2
| SCO |  |  | SCO's philosophy and intent | SCO's CCIRs/SIRs | T-2
|  |  | Receive Counseling from SCO, finish initial draft of support form |  |  | T-2
Attend training meetings
| Arms Rm NCO |  | Meet with Arms Room NCO to discuss issues/ideas |  |  | T-2
|  |  | Develop/Obtain/Prepare the following: |  |  | T-1
|  |  |  | OER Support Form | Troop CCIRs/SIRs | T-1
|  |  |  | Business cards | Family Letter of Introduction | T-1
|  |  |  | Organizational Inbrief | Initial Counseling Forms | T-1
|  |  |  | Initial Policy Letters |  | T-1
| 1SG |  | Review Troop Welcome/New Soldier Packet |  |  | T-1
|  |  | Discuss Troop affairs and NCO issues |  |  | T-1
| Ops |  | Prepare Assumption of Command memorandum |  |  | D-1
| Ops/All |  | Conduct PAI and check SRF, military driver's licenses, and FCPs (re-sign all) |  |  | D-1
Initial Assessment Period (D-Day to D+30) | S1/S4 |  | Sign assumption of command orders |  |  | D
| Various |  |  | Attend CoC Ceremony | Meet with Key Leaders | D
Get the vitals of office
|  |  | Issue Command Team Philosophy |  |  | D+1
| Supply Sergeant |  | Close out Troop inventories and SHRs |  |  | T Week
| Ops/EOR |  | Request: |  |  | T Week
|  |  |  | ICI (within next 8 weeks) | Command Climate Survey
| Subordinates |  | Counsel Direct Subordinates/Key Leaders: |  |  | T Week
Analyze short/long term personal/professional goals
Determine thoughts and feelings about the unit
See what they need help with individually and professionally
| Operations |  | Update: |  |  | T Week
|  |  |  | Alert Roster | Social Roster
|  |  |  | Rating Scheme | Family Care Plans
|  |  |  | Troop METL | Hand Receipt Holders
| 1SG |  | Conduct Organizational Inbrief |  |  | T Week
| Unit UPL |  | Conduct Unit Urinalysis |  |  | T+3
| Mixed |  | Meet with/Conduct: |  |  | T+3 to T+4
|  |  |  | Staff (OICs/PBO/Maint) | Supply SGT (issues)
|  |  |  | Review last 2 APFTs w/ 1SG | Chaplain
|  |  |  | Soldier Support Activities | Conduct DEOCS/Sensing Session
| 1SG |  | Establish Leader Development Program |  |  | T+4
Organizational Alignment and Team Building (D+30 to D+60) | Ops/Tng |  | Review Training Points of Contact |  |  | T+5
| 1SG, Ops, Tng |  | Establish Battle Rhythm: |  |  | T+5
|  |  |  | SQDN Requirements | SQDN Reports, etc
Training Meeting
| 1SG |  | Conduct APFT |  |  | T+5
| Retention NCO |  | Meet with Retention NCO to determine retention rates |  |  | T+6
| Subordinates |  | Meet subordinates about training calendar |  |  | T+6
Conduct ICI
| 1SG |  | Develop Next Quarter Plan of Action based on assessment |  |  | T+8